## Sheet1
Issue # | User story/Task title | Story points | Due date | Associated tasks/Task description | Priority (low, medium, high) | Risk (low, medium, high) | Responsible
Sprint 1
US.01: As an instructor, I want to create an account
27 | Task 01.01: Implement a webpage form for instructor to sign up | 3 | 23/09/2024 | Develop the frontend form for instructor sign-up using React | High | High | Mark
28 | Task 01.02: Save data in React (name, email, pass, sections) | 3 | 20/09/2024 | Store the instructor's data (name, email, password, sections) in React state | High | High | Mark
29 | Task 01.03: Receive data using API, make object of student and add it to CSV | 5 | 20/09/2024 | Use API to receive instructor data, create objects, and append to CSV | High | High | Anthony
40 | Task 01.04: Implement back-end structure (required classes) | 8 | 20/09/2024 | Develop the back-end structure with necessary classes for handling the data | High | High | Mark
US.02: As a student, I want to create an account
13 | Task 02.01: Implement a webpage form for students to sign up | 3 | 23/09/2024 | Develop the frontend form for student sign-up using React | High | Medium | Anthony
14 | Task 02.02: Save data in React (name, email, pass, sections) | 3 | 23/09/2024 | Store student's data (name, email, password, sections) in React state | High | High | Mark
15 | Task 02.03: Receive data using API, make object of student and add to CSV | 8 | 23/09/2024 | Receive student data through API, create objects and append to CSV | High | High | Mark
US.03: As student or instructor, we want to log in
17 | Task 03.01: Make log-in webpage for student and instructor | 5 | 23/09/2024 | Create log-in webpage (email, password, checkbox for role) | High | Medium | DaniK1001
18 | Task 03.02: Send log-in info to Spring Boot (front end) | 8 | 23/09/2024 | Send log-in information from front end to Spring Boot backend | High | High | DaniK1001
19 | Task 03.03: Verify log-in credentials | 5 | 23/09/2024 | Verify log-in information in the backend and confirm account exists | Medium | High | Lemonada10
20 | Task 03.04: If account exists, send necessary info to frontend | 3 | 23/09/2024 | Send account info back to frontend for display | High | Medium | Lemonada10
22 | Task 03.05: If account does not exist, display error | 2 | 23/09/2024 | Show error message when login info is invalid | Medium | Medium | DaniK1001
US.04: As a student, I want to see all my class teams and team members
37 | Task 04.01: Create frontend UI to display class teams | 5 | 26/09/2024 | Create UI to show list of teams to the student | Medium | Medium | Anthony
38 | Task 04.02: Develop backend to retrieve class teams for the student | 8 | 26/09/2024 | Retrieve all class teams from the backend for the logged-in student | High | High | DaniK1001
39 | Task 04.03: Handle case where student is not assigned to a team | 3 | 26/09/2024 | Create functionality to handle cases where the student is not assigned to any team | Medium | Medium | Lemonada10
US.05: As an instructor, I want to see all teams and team members
31 | Task 05.01: Receive data from backend for instructor teams | 8 | 23/09/2024 | Receive data from the backend, including team and member info for the instructor | High | High | Ren-cc
32 | Task 05.02: Display teams and members on the webpage | 3 | 23/09/2024 | Display instructor's teams and members on the UI | High | Medium | Ren-cc
US.06: As an instructor, I want to manage students in teams
34 | Task 06.01: Display teams and allow instructor to manage them | 5 | 26/09/2024 | Show all teams and allow the instructor to choose a team to manage | Medium | Medium | Ren-cc
35 | Task 06.02: Allow deleting students from teams | 3 | 26/09/2024 | Instructor can delete students from the selected team | High | Medium | Ren-cc
36 | Task 06.03: Add unassigned students to a team | 3 | 26/09/2024 | Allow instructor to add students that are not assigned to any team | Medium | High | Ren-cc
Sprint 2
US.07: As a student using the peer evaluation platform, I want a simple and intuitive interface to select my teammates for evaluation so that I can efficiently assess their contributions and provide feedback.(sp:4)
83 | Task 07.01 After selecting teammates, students should be redirected to the evaluation form. | 1 | 10/10/2024 | Create navigation to redirect the student to the evaluation form page upon selecting teammates. | Medium | Low | Anthony
93 | Task 07.02 Modify/design the evaluation form page. | 3 | 10/10/2024 | Design the evaluation form interface, including options for selecting teammates, providing ratings, and submitting feedback. | High | Medium | Ren-cc
US.08: As a student, I want to assess my teammates across multiple dimensions—Cooperation, Conceptual Contribution, Practical Contribution, and Work Ethic—so I can provide a more comprehensive evaluation of their performance.(sp10)
84 | Task.08.01 The evaluation form should include the following dimensions for each teammate: Cooperation Conceptual Contribution Practical Contribution Work Ethic. | 1 | 24/10/2024 | Develop a form with fields for Cooperation, Conceptual Contribution, Practical Contribution, and Work Ethic. | High | Medium | Anthony
85 | Task.08.02 Each dimension should have a 5-point rating scale (1 to 5). | 0 | 24/10/2024 | Add a rating scale input (1-5) for each dimension in the form. | Medium | Low | Anthony
86 | Task.08.03 For each dimension, provide an optional comment box where students can add qualitative feedback. | 0 | 24/10/2024 | Include comment boxes below each rating scale to capture optional feedback. | Low | Low | Anthony
87 | Task.08.04 Ensure that comments are optional and do not affect the ability to submit ratings. | 1 | 24/10/2024 | Adjust form validation to allow submission without comments. | Medium | Low | Anthony
88 | Task.08.05 The system should validate that all teammates have been rated across all dimensions before submission. | 3 | 24/10/2024 | Implement form validation to ensure every teammate is rated on each dimension before submission. | High | Medium | Anthony
89 | Task.08.06 After completing the assessment, students should see a confirmation page summarizing both ratings and comments (if provided). | 3 | 24/10/2024 | Display a summary page with details of the student's ratings and comments for each teammate. | High | Medium | Anthony
94 | Task.08.07 Design confirmation page. | 1 | 24/10/2024 | Design the layout of the confirmation page to display the teammate assessments clearly. | Medium | Low | Ren-cc
90 | Task.08.08 Once confirmed, students should receive a success message indicating their evaluation has been submitted. | 0 | 24/10/2024 | Show a success message after the confirmation page, confirming the evaluation submission. | Medium | Low | Anthony
US.09 As a developer, I want to store user and assessment data in a PostgreSQL database, so that the system can scale and provide robust data management while keeping the API unchanged for the frontend.(sp:26)
75 | Task.09.01 Set up PostgreSQL database | 8 | 21/10/2024 | Configure PostgreSQL server, create schema, and set up initial tables. | High | High | Lemonada10
76 | Task.09.02 Update Spring Boot configuration | 3 | 21/10/2024 | Configure Spring Boot to connect with PostgreSQL and manage database sessions. | High | High | Lemonada10
77 | Task.09.03 Define JPA entities | 1 | 21/10/2024 | Define JPA entity classes corresponding to the tables for storing users and assessments. | Medium | Medium | Lemonada10
78 | Task.09.04 Implement Spring Data JPA Repositories | 3 | 21/10/2024 | Create repository interfaces to interact with user and assessment data in PostgreSQL. | Medium | Medium | Lemonada10
79 | Task.09.05 Refactor Service Layer | 8 | 21/10/2024 | Implement security configurations to protect database access and prevent unauthorized modifications. | High | High | Lemonada10
80 | Task.09.06 Test API Compatibility | 3 | 21/10/2024 | Run tests to ensure that the new PostgreSQL setup functions with the existing API without breaking changes. | High | Medium | Lemonada10
US.10 As a developer, I want to ensure that the frontend React app continues to function without changes, so that the migration to PostgreSQL is seamless and transparent to users.(sp:4)
91 | Task.10.01 Test React app with migrated backend | 3 | 25/10/2024 | Verify that all frontend components continue to work as expected with the PostgreSQL database. | High | Medium | Lemonada10
92 | Task.10.02 Verify frontend data handling | 1 | 25/10/2024 | Test data retrieval and submission functions in the frontend to ensure compatibility with PostgreSQL. | Medium | Low | Lemonada10
US.11 As a developer, I want to make unit testing to make sure that all back-end functionalities are working/behaving as expected.(sp:14)
96 | Task.11.01 Implement unit testing for sign up | 5 | 27/10/2024 | Create unit tests for user sign-in functionality, ensuring security and data accuracy. | High | Medium | Mark
97 | Task.11.02 Implement unit testing for sign in | 3 | 27/10/2024 | Develop unit tests for user sign-up, verifying data integrity and validation rules. | High | Medium | DaniK1001
98 | Task.11.03 Implement unit testing for database | 3 | 27/10/2024 | Create unit tests for fetching and modifying student information. | High | High | Mark, DaniK1001, Anthony
99 | Task11.04 Implement CI/CD pipeline and connect it to back-end unit tests in order for automatic testing when merging branches | 3 | 27/10/2024 | Configure CI/CD pipeline to automatically run back-end unit tests upon code integration. | High | High | Lemonada10
PLEASE REFER TO GITHUB FOR THE ACCEPTANCE CRITERIA