## Sheet1
Issue # | User story/Task title | Story points | Due date | Associated tasks/Task description | Priority (low, medium, high) | Risk (low, medium, high) | Responsible
Sprint 1
US.01: As an instructor, I want to create an account
27 | Task 01.01: Implement a webpage form for instructor to sign up | 3 | 23/09/2024 | Develop the frontend form for instructor sign-up using React | High | High | Mark
28 | Task 01.02: Save data in React (name, email, pass, sections) | 3 | 20/09/2024 | Store the instructor's data (name, email, password, sections) in React state | High | High | Mark
29 | Task 01.03: Receive data using API, make object of student and add it to CSV | 5 | 20/09/2024 | Use API to receive instructor data, create objects, and append to CSV | High | High | Anthony
40 | Task 01.04: Implement back-end structure (required classes) | 8 | 20/09/2024 | Develop the back-end structure with necessary classes for handling the data | High | High | Mark
US.02: As a student, I want to create an account
13 | Task 02.01: Implement a webpage form for students to sign up | 3 | 23/09/2024 | Develop the frontend form for student sign-up using React | High | Medium | Anthony
14 | Task 02.02: Save data in React (name, email, pass, sections) | 3 | 23/09/2024 | Store student's data (name, email, password, sections) in React state | High | High | Mark
15 | Task 02.03: Receive data using API, make object of student and add to CSV | 8 | 23/09/2024 | Receive student data through API, create objects and append to CSV | High | High | Mark
US.03: As student or instructor, we want to log in
17 | Task 03.01: Make log-in webpage for student and instructor | 5 | 23/09/2024 | Create log-in webpage (email, password, checkbox for role) | High | Medium | DaniK1001
18 | Task 03.02: Send log-in info to Spring Boot (front end) | 8 | 23/09/2024 | Send log-in information from front end to Spring Boot backend | High | High | DaniK1001
19 | Task 03.03: Verify log-in credentials | 5 | 23/09/2024 | Verify log-in information in the backend and confirm account exists | Medium | High | Lemonada10
20 | Task 03.04: If account exists, send necessary info to frontend | 3 | 23/09/2024 | Send account info back to frontend for display | High | Medium | Lemonada10
22 | Task 03.05: If account does not exist, display error | 2 | 23/09/2024 | Show error message when login info is invalid | Medium | Medium | DaniK1001
US.04: As a student, I want to see all my class teams and team members
37 | Task 04.01: Create frontend UI to display class teams | 5 | 26/09/2024 | Create UI to show list of teams to the student | Medium | Medium | Anthony
38 | Task 04.02: Develop backend to retrieve class teams for the student | 8 | 26/09/2024 | Retrieve all class teams from the backend for the logged-in student | High | High | DaniK1001
39 | Task 04.03: Handle case where student is not assigned to a team | 3 | 26/09/2024 | Create functionality to handle cases where the student is not assigned to any team | Medium | Medium | Lemonada10
US.05: As an instructor, I want to see all teams and team members
31 | Task 05.01: Receive data from backend for instructor teams | 8 | 23/09/2024 | Receive data from the backend, including team and member info for the instructor | High | High | Ren-cc
32 | Task 05.02: Display teams and members on the webpage | 3 | 23/09/2024 | Display instructor's teams and members on the UI | High | Medium | Ren-cc
US.06: As an instructor, I want to manage students in teams
34 | Task 06.01: Display teams and allow instructor to manage them | 5 | 26/09/2024 | Show all teams and allow the instructor to choose a team to manage | Medium | Medium | Ren-cc
35 | Task 06.02: Allow deleting students from teams | 3 | 26/09/2024 | Instructor can delete students from the selected team | High | Medium | Ren-cc
36 | Task 06.03: Add unassigned students to a team | 3 | 26/09/2024 | Allow instructor to add students that are not assigned to any team | Medium | High | Ren-cc