## Sheet1
Issue # | User story/Task title | Story points | Due date | Associated tasks/Task description | Priority (low, medium, high) | Risk (low, medium, high) | Responsible
Sprint 1
US.01: As an instructor, I want to create an account
27 | Task 01.01: Implement a webpage form for instructor to sign up | 3 | 23/09/2024 | Develop the frontend form for instructor sign-up using React | High | High | Mark
28 | Task 01.02: Save data in React (name, email, pass, sections) | 3 | 20/09/2024 | Store the instructor's data (name, email, password, sections) in React state | High | High | Mark
29 | Task 01.03: Receive data using API, make object of student and add it to CSV | 5 | 20/09/2024 | Use API to receive instructor data, create objects, and append to CSV | High | High | Anthony
40 | Task 01.04: Implement back-end structure (required classes) | 8 | 20/09/2024 | Develop the back-end structure with necessary classes for handling the data | High | High | Mark
US.02: As a student, I want to create an account
13 | Task 02.01: Implement a webpage form for students to sign up | 3 | 23/09/2024 | Develop the frontend form for student sign-up using React | High | Medium | Anthony
14 | Task 02.02: Save data in React (name, email, pass, sections) | 3 | 23/09/2024 | Store student's data (name, email, password, sections) in React state | High | High | Mark
15 | Task 02.03: Receive data using API, make object of student and add to CSV | 8 | 23/09/2024 | Receive student data through API, create objects and append to CSV | High | High | Mark
US.03: As student or instructor, we want to log in
17 | Task 03.01: Make log-in webpage for student and instructor | 5 | 23/09/2024 | Create log-in webpage (email, password, checkbox for role) | High | Medium | DaniK1001
18 | Task 03.02: Send log-in info to Spring Boot (front end) | 8 | 23/09/2024 | Send log-in information from front end to Spring Boot backend | High | High | DaniK1001
19 | Task 03.03: Verify log-in credentials | 5 | 23/09/2024 | Verify log-in information in the backend and confirm account exists | Medium | High | Lemonada10
20 | Task 03.04: If account exists, send necessary info to frontend | 3 | 23/09/2024 | Send account info back to frontend for display | High | Medium | Lemonada10
22 | Task 03.05: If account does not exist, display error | 2 | 23/09/2024 | Show error message when login info is invalid | Medium | Medium | DaniK1001
US.04: As a student, I want to see all my class teams and team members
37 | Task 04.01: Create frontend UI to display class teams | 5 | 26/09/2024 | Create UI to show list of teams to the student | Medium | Medium | Anthony
38 | Task 04.02: Develop backend to retrieve class teams for the student | 8 | 26/09/2024 | Retrieve all class teams from the backend for the logged-in student | High | High | DaniK1001
39 | Task 04.03: Handle case where student is not assigned to a team | 3 | 26/09/2024 | Create functionality to handle cases where the student is not assigned to any team | Medium | Medium | Lemonada10
US.05: As an instructor, I want to see all teams and team members
31 | Task 05.01: Receive data from backend for instructor teams | 8 | 23/09/2024 | Receive data from the backend, including team and member info for the instructor | High | High | Ren-cc
32 | Task 05.02: Display teams and members on the webpage | 3 | 23/09/2024 | Display instructor's teams and members on the UI | High | Medium | Ren-cc
US.06: As an instructor, I want to manage students in teams
34 | Task 06.01: Display teams and allow instructor to manage them | 5 | 26/09/2024 | Show all teams and allow the instructor to choose a team to manage | Medium | Medium | Ren-cc
35 | Task 06.02: Allow deleting students from teams | 3 | 26/09/2024 | Instructor can delete students from the selected team | High | Medium | Ren-cc
36 | Task 06.03: Add unassigned students to a team | 3 | 26/09/2024 | Allow instructor to add students that are not assigned to any team | Medium | High | Ren-cc
Sprint 2
US.07: As a student using the peer evaluation platform, I want a simple and intuitive interface to select my teammates for evaluation so that I can efficiently assess their contributions and provide feedback.(sp:4)
83 | Task 07.01 After selecting teammates, students should be redirected to the evaluation form. | 1 | 10/10/2024 | Create navigation to redirect the student to the evaluation form page upon selecting teammates. | Medium | Low | Anthony
93 | Task 07.02 Modify/design the evaluation form page. | 3 | 10/10/2024 | Design the evaluation form interface, including options for selecting teammates, providing ratings, and submitting feedback. | High | Medium | Ren-cc
US.08: As a student, I want to assess my teammates across multiple dimensions—Cooperation, Conceptual Contribution, Practical Contribution, and Work Ethic—so I can provide a more comprehensive evaluation of their performance.(sp10)
84 | Task.08.01 The evaluation form should include the following dimensions for each teammate: Cooperation Conceptual Contribution Practical Contribution Work Ethic. | 1 | 24/10/2024 | Develop a form with fields for Cooperation, Conceptual Contribution, Practical Contribution, and Work Ethic. | High | Medium | Anthony
85 | Task.08.02 Each dimension should have a 5-point rating scale (1 to 5). | 0 | 24/10/2024 | Add a rating scale input (1-5) for each dimension in the form. | Medium | Low | Anthony
86 | Task.08.03 For each dimension, provide an optional comment box where students can add qualitative feedback. | 0 | 24/10/2024 | Include comment boxes below each rating scale to capture optional feedback. | Low | Low | Anthony
87 | Task.08.04 Ensure that comments are optional and do not affect the ability to submit ratings. | 1 | 24/10/2024 | Adjust form validation to allow submission without comments. | Medium | Low | Anthony
88 | Task.08.05 The system should validate that all teammates have been rated across all dimensions before submission. | 3 | 24/10/2024 | Implement form validation to ensure every teammate is rated on each dimension before submission. | High | Medium | Anthony
89 | Task.08.06 After completing the assessment, students should see a confirmation page summarizing both ratings and comments (if provided). | 3 | 24/10/2024 | Display a summary page with details of the student's ratings and comments for each teammate. | High | Medium | Anthony
94 | Task.08.07 Design confirmation page. | 1 | 24/10/2024 | Design the layout of the confirmation page to display the teammate assessments clearly. | Medium | Low | Ren-cc
90 | Task.08.08 Once confirmed, students should receive a success message indicating their evaluation has been submitted. | 0 | 24/10/2024 | Show a success message after the confirmation page, confirming the evaluation submission. | Medium | Low | Anthony
US.09 As a developer, I want to store user and assessment data in a PostgreSQL database, so that the system can scale and provide robust data management while keeping the API unchanged for the frontend.(sp:26)
75 | Task.09.01 Set up PostgreSQL database | 8 | 21/10/2024 | Configure PostgreSQL server, create schema, and set up initial tables. | High | High | Lemonada10
76 | Task.09.02 Update Spring Boot configuration | 3 | 21/10/2024 | Configure Spring Boot to connect with PostgreSQL and manage database sessions. | High | High | Lemonada10
77 | Task.09.03 Define JPA entities | 1 | 21/10/2024 | Define JPA entity classes corresponding to the tables for storing users and assessments. | Medium | Medium | Lemonada10
78 | Task.09.04 Implement Spring Data JPA Repositories | 3 | 21/10/2024 | Create repository interfaces to interact with user and assessment data in PostgreSQL. | Medium | Medium | Lemonada10
79 | Task.09.05 Refactor Service Layer | 8 | 21/10/2024 | Implement security configurations to protect database access and prevent unauthorized modifications. | High | High | Lemonada10
80 | Task.09.06 Test API Compatibility | 3 | 21/10/2024 | Run tests to ensure that the new PostgreSQL setup functions with the existing API without breaking changes. | High | Medium | Lemonada10
US.10 As a developer, I want to ensure that the frontend React app continues to function without changes, so that the migration to PostgreSQL is seamless and transparent to users.(sp:4)
91 | Task.10.01 Test React app with migrated backend | 3 | 25/10/2024 | Verify that all frontend components continue to work as expected with the PostgreSQL database. | High | Medium | Lemonada10
92 | Task.10.02 Verify frontend data handling | 1 | 25/10/2024 | Test data retrieval and submission functions in the frontend to ensure compatibility with PostgreSQL. | Medium | Low | Lemonada10
US.11 As a developer, I want to make unit testing to make sure that all back-end functionalities are working/behaving as expected.(sp:14)
96 | Task.11.01 Implement unit testing for sign up | 5 | 27/10/2024 | Create unit tests for user sign-in functionality, ensuring security and data accuracy. | High | Medium | Mark
97 | Task.11.02 Implement unit testing for sign in | 3 | 27/10/2024 | Develop unit tests for user sign-up, verifying data integrity and validation rules. | High | Medium | DaniK1001
98 | Task.11.03 Implement unit testing for database | 3 | 27/10/2024 | Create unit tests for fetching and modifying student information. | High | High | Mark, DaniK1001, Anthony
99 | Task11.04 Implement CI/CD pipeline and connect it to back-end unit tests in order for automatic testing when merging branches | 3 | 27/10/2024 | Configure CI/CD pipeline to automatically run back-end unit tests upon code integration. | High | High | Lemonada10
Sprint 3
US.12 As a developer, I want the peer evaluation review to be stored in the database (sp:5)
119 | Task 12.01: Implement frontend API to send review data to backend | 1 | 01/11/2024 | Develop a frontend API to send peer evaluation review data from the client side to the Develop a frontend API to send peer evaluation review data from the client side to the backend server. | High | Medium | Lemonada10
120 | Task 12.02: Create database schema for peer evaluation review | 3 | 01/11/2024 | Design the database schema to store peer evaluation review data, ensuring that the schema can handle all required fields and relationships. | High | High | DaniK1001
121 | Task 12.03: Implement backend API to handle peer evaluation review storage | 1 | 01/11/2024 | Build a backend API endpoint to receive review data from the frontend and save it in the database. | High | High | DaniK1001
US.013: As an instructor, I want to view a summary of all assessments (sp:6)
126 | Task 13.01: Design summary view UI on main dashboard | 1 | 04/11/2024 | Develop a user interface for the main dashboard that provides a summary view of all assessments for instructors. | High | Medium | Ren-cc
127 | Task 13.02: Implement calculation of average scores for each category | 3 | 04/11/2024 | Create functionality to calculate average scores for each assessment category, such as teamwork, communication, etc. | High | High | Anthony
128 | Task 13.03: Display count of completed assessments in summary view | 1 | 04/11/2024 | Show the number of completed assessments in the summary view to help instructors track assessment completion. | Medium | Low | Anthony
129 | Task 13.04: Connect Backend API to summary view for data retrieval | 1 | 04/11/2024 | Integrate backend API to fetch and display assessment data in the summary view UI. | High | Medium | Mark
US.14 As an instructor, I want to view detailed results of individual assessments (sp:8)
131 | Task 14.01: Design detailed assessment view layout | 3 | 06/11/2024 | Develop a UI layout for viewing detailed results of individual assessments. | High | Medium | Ren-cc
132 | Task 14.02: Display individual scores and comments for each assessment | 3 | 06/11/2024 | Implement functionality to display individual scores and instructor comments for each assessment in detail. | High | Medium | Anthony
133 | Task 14.03: Enable navigation from summary view to detailed view | 1 | 06/11/2024 | Add a navigation feature to allow instructors to click on an item in the summary view and see the detailed assessment. | Medium | Low | Anthony
134 | Task 14.05: Connect detailed view to backend API to retrieve data | 1 | 06/11/2024 | Integrate backend API to fetch and display detailed assessment data. | High | Medium | Mark
US.15 As a developer, I want to create unit tests for key components and functions (sp:21)
136 | Task 15.01: Write unit tests for average score calculation function | 3 | 08/11/2024 | Develop unit tests to verify the accuracy of the average score calculation function. | High | Medium | Lemonada10
137 | Task 15.02: Write unit tests for displaying count of completed assessments | 3 | 08/11/2024 | Create tests to verify that the count of completed assessments is displayed accurately. | Medium | Low | Lemonada10
138 | Task 15.03: Write unit tests for individual assessment display function | 3 | 08/11/2024 | Develop tests for the functionality that displays individual assessment details. | High | Medium | Lemonada10
139 | Task 15.04: Write unit tests for student and instructor sign in(front-end) | 3 | 08/11/2024 | Test back-end user sign-in functionality to ensure security and validation. | High | Medium | Lemonada10
140 | Task 15.05: Write unit tests for student and instructor sign up (front-end) | 3 | 08/11/2024 | Create tests to validate the front-end user sign-up process, ensuring that inputs are correctly handled and errors are displayed for invalid entries. | High | Medium | Lemonada10
141 | Task 15.06: Write unit tests for student and instructor sign up (back-end) | 3 | 08/11/2024 | Develop back-end tests for user sign-up functionality, ensuring proper validation and storage of user data in the database. | High | High | Mark
142 | Task 15.07: Write unit tests for student and instructor sign in (back-end) | 3 | 08/11/2024 | Develop unit tests for back-end sign-in functionality, ensuring validation of user credentials and secure authentication. | High | High | DaniK1001
143 | Task 15.08: Write unit tests for all controllers in java | 3 | 08/11/2024 | Implement unit tests for all back-end controllers, ensuring that they handle requests correctly and respond with appropriate data or error messages. | High | High | DaniK1001
US.16 As a developer, I want to limit profanity in comments and add email confirmation for signup (sp:5)
167 | Task 16.01: Implement sentiment analysis for comment fields | 3 | 10/11/2024 | Add a filtering mechanism to detect and limit profanity in comments. | Medium | Medium | DaniK1001
168 | Task 16.02: Implement mail sending algorithm in backend | 2 | 10/11/2024 | Develop a backend algorithm to send email confirmations for user signups. | High | High | Mark
Sprint 4
US.17 As a developer, I want to integrate SonarQube so that I can have code analysis reports.(SP:20)
175 | Task 17.01: Create sonar-project.properties file | 5 | 11/25/2024 | Create and configure the sonar-project.properties file to define project-specific settings, including project key, source directory, and SonarQube server details. | High | Low | Lemonada10
176 | Task 17.02: Create a new GitHub Actions workflow YAML file (.github/workflows/sonar.yml) | 8 | 11/25/2024 | Create a GitHub Actions workflow file to automate SonarQube analysis during the CI/CD pipeline, ensuring code is scanned for quality checks after every commit or pull request. | High | High | Lemonada10
177 | Task 17.03: Configure SonarQube Quality Gates | 5 | 11/25/2024 | Set up quality gates in SonarQube to define thresholds for code quality metrics such as code coverage, bugs, vulnerabilities, and code smells. | Medium | Low | Lemonada10
179 | Task 17.05: Test Notification Setup | 2 | 11/25/2024 | Verify the notification system by testing SonarQube alerts for events such as quality gate failures, new issues, or analysis results, and ensure notifications are delivered to relevant team members. | Low | Medium | Lemonada10
UAT.16 As a developer, I want to make acceptance tests for the AI feature (SP:3)
202 | Write acceptance test in react using cypress | 3 | 11/25/2024 | Write Cypress tests to validate key user workflows in the React app, ensuring proper functionality and expected behavior. | High | Low | DaniK1001
ENH.02 As a developer, I want to improve front-end user experience by making the website load faster and include visuals for easier understanding (SP:4)
158 | Task.02.01: implement colors to summary view to describe review grade (1-2 = red, 3 = yellow, 4,5 = green) | 1 | 11/25/2024 | Add a color-coded system (red, yellow, green) to the summary view to visually represent review grades based on their scores. | Low | Low | Ren-cc
159 | Task.02.02: make background animation a video to make the website run faster. | 2 | 11/25/2024 | Replace the animated background with a lightweight video to improve website performance and loading speed. | High | Medium | Ren-cc
160 | Task.02.03: add table student sorting depending on users preference | 1 | 11/25/2024 | Enable sorting functionality in the student table based on user-selected criteria, such as name, grade, or review date. | Low | Low | Ren-cc
ENH.03 As a developer, I want to give the user the option to go back a page (SP:2)
173 | Implement new button for user to go back to previous page | 2 | 11/25/2024 | Replace the animated background with a lightweight video to improve website performance and loading speed. | High | Medium | Ren-cc
ENH.04 As a developer, I want to improve profanity detection when writing a comment for a student review (SP:2)
181 | Implement new AI library that better works for bad word detection and sentiment analysis using TensorFlow | 2 | 11/25/2024 | Enable sorting functionality in the student table based on user-selected criteria, such as name, grade, or review date. | Medium | Medium | DaniK1001
ENH.05 As a developer, I want to implement email confirmation when a new user signs up. (SP:5)
183 | Task.05.01: Create an email for makesoft that will be responsible for sending the confirmation | 0 | 11/25/2024 | Create a dedicated email account for the MakeSoft application to handle sending confirmation emails to users. | High | Low | Mark
184 | Task.05.02: Add SMTP configuration to application.properties or application.yml (e.g., SMTP host, port, username, password). | 2 | 11/25/2024 | Add SMTP server details, including host, port, credentials, and other required settings, to the application configuration file for email functionality. | High | Medium | Mark
185 | Task.05.03: Create a EmailService class that uses JavaMailSender for sending emails. | 1 | 11/25/2024 | Implement a service class in Spring Boot to handle email-sending operations using the JavaMailSender API. | High | Medium | Mark
186 | Task.05.04: Implement a method to send a basic text email (e.g., sendEmail(String to, String subject, String text)). | 0 | 11/25/2024 | Add a method to the EmailService class to send simple text-based emails with recipient, subject, and message body as parameters. | Medium | Low | Mark
187 | Task.05.05: Configure JavaMailSender bean in a Spring Boot configuration class. | 1 | 11/25/2024 | Configure a JavaMailSender bean in a Spring Boot configuration class to enable email-sending capabilities. | Medium | Low | Mark
188 | Task.05.06: Modify the user registration flow to call the EmailService.sendEmail() method after a user successfully registers. | 1 | 11/25/2024 | Update the user registration logic to include a call to the EmailService for sending a confirmation email after successful registration. | High | Medium | Mark
ENH.06 As a student, I want to receive an email when I am placed in a team by the instructor in order to know when to review my teammates (SP:2)
195 | Task.05.01 Write a service that sends an email to students when the team placement event is triggered. | 1 | 11/25/2024 | Develop a service to automatically send emails to students upon triggering the team placement event. | High | Medium | Mark
194 | Task.05.02 Create a templated email message that informs students of their team placement and provides any necessary instructions. | 1 | 11/25/2024 | Design an email template to notify students of their team assignment and include relevant instructions or details. | Medium | Low | Mark
ENH.07 As a developer, I want to improve the CI/CD pipeline in order to have better maintenability and scalability (SP:5)
204 | ENH.07.01 Refactor the existing CI/CD pipeline YAML file to separate the workflow into distinct steps: build, test, and deploy. Each step should have its own job to ensure clarity, maintainability, and better debugging capabilities. The refactored pipeline should preserve all current functionality and allow steps to run independently or sequentially as needed. | 5 | 11/25/2024 | Refactor the CI/CD pipeline YAML file to separate the workflow into distinct jobs for build, test, and deploy, improving clarity and maintainability while preserving existing functionality. | High | Medium | Anthony
BUG.01. As a developer, I want to fix the student sign up to successfully describe whether the student signed up successfully (SP:2)
170 | Task.01.01: fix success message after invalid student sign up | 1 | 11/25/2024 | Develop a service to automatically send emails to students upon triggering the team placement event. | High | Medium | Ren-cc
171 | Task.01.02: Ensure that the email REGEX works properly for sign up and sign in | 1 | 11/25/2024 | Design an email template to notify students of their team assignment and include relevant instructions or details. | Medium | Low | Ren-cc
Bug.02: As a developer, I want to fix the Instructor sign up to successfully describe whether the Instructor signed up successfully (SP:2)
190 | Fix Sign up messages | 1 | 11/25/2024 | Correct and improve the messages displayed during the sign-up process to ensure clarity and better user experience. | High | Low | Ren-cc
191 | Ensure that the email REGEX works properly for sign up and sign in | 1 | 11/25/2024 | Update and verify the regular expression (REGEX) used for email validation in both the sign-up and sign-in processes to ensure it properly checks valid email formats. | High | Medium | Ren-cc
PLEASE REFER TO GITHUB FOR THE ACCEPTANCE CRITERIA