## Sheet1
Issue # | User story/Task title | Story points | Due date | Associated tasks/Task description | Priority (low, medium, high) | Risk (low, medium, high) | Responsible
Sprint 1
US.01: As an instructor, I want to create an account
27 | Task 01.01: Implement a webpage form for instructor to sign up | 3 | 23/09/2024 | Develop the frontend form for instructor sign-up using React | High | High | Mark
28 | Task 01.02: Save data in React (name, email, pass, sections) | 3 | 20/09/2024 | Store the instructor's data (name, email, password, sections) in React state | High | High | Mark
29 | Task 01.03: Receive data using API, make object of student and add it to CSV | 5 | 20/09/2024 | Use API to receive instructor data, create objects, and append to CSV | High | High | Anthony
40 | Task 01.04: Implement back-end structure (required classes) | 8 | 20/09/2024 | Develop the back-end structure with necessary classes for handling the data | High | High | Mark
US.02: As a student, I want to create an account
13 | Task 02.01: Implement a webpage form for students to sign up | 3 | 23/09/2024 | Develop the frontend form for student sign-up using React | High | Medium | Anthony
14 | Task 02.02: Save data in React (name, email, pass, sections) | 3 | 23/09/2024 | Store student's data (name, email, password, sections) in React state | High | High | Mark
15 | Task 02.03: Receive data using API, make object of student and add to CSV | 8 | 23/09/2024 | Receive student data through API, create objects and append to CSV | High | High | Mark
US.03: As student or instructor, we want to log in
17 | Task 03.01: Make log-in webpage for student and instructor | 5 | 23/09/2024 | Create log-in webpage (email, password, checkbox for role) | High | Medium | DaniK1001
18 | Task 03.02: Send log-in info to Spring Boot (front end) | 8 | 23/09/2024 | Send log-in information from front end to Spring Boot backend | High | High | DaniK1001
19 | Task 03.03: Verify log-in credentials | 5 | 23/09/2024 | Verify log-in information in the backend and confirm account exists | Medium | High | Lemonada10
20 | Task 03.04: If account exists, send necessary info to frontend | 3 | 23/09/2024 | Send account info back to frontend for display | High | Medium | Lemonada10
22 | Task 03.05: If account does not exist, display error | 2 | 23/09/2024 | Show error message when login info is invalid | Medium | Medium | DaniK1001
US.04: As a student, I want to see all my class teams and team members
37 | Task 04.01: Create frontend UI to display class teams | 5 | 26/09/2024 | Create UI to show list of teams to the student | Medium | Medium | Anthony
38 | Task 04.02: Develop backend to retrieve class teams for the student | 8 | 26/09/2024 | Retrieve all class teams from the backend for the logged-in student | High | High | DaniK1001
39 | Task 04.03: Handle case where student is not assigned to a team | 3 | 26/09/2024 | Create functionality to handle cases where the student is not assigned to any team | Medium | Medium | Lemonada10
US.05: As an instructor, I want to see all teams and team members
31 | Task 05.01: Receive data from backend for instructor teams | 8 | 23/09/2024 | Receive data from the backend, including team and member info for the instructor | High | High | Ren-cc
32 | Task 05.02: Display teams and members on the webpage | 3 | 23/09/2024 | Display instructor's teams and members on the UI | High | Medium | Ren-cc
US.06: As an instructor, I want to manage students in teams
34 | Task 06.01: Display teams and allow instructor to manage them | 5 | 26/09/2024 | Show all teams and allow the instructor to choose a team to manage | Medium | Medium | Ren-cc
35 | Task 06.02: Allow deleting students from teams | 3 | 26/09/2024 | Instructor can delete students from the selected team | High | Medium | Ren-cc
36 | Task 06.03: Add unassigned students to a team | 3 | 26/09/2024 | Allow instructor to add students that are not assigned to any team | Medium | High | Ren-cc
Sprint 2
US.07: As a student using the peer evaluation platform, I want a simple and intuitive interface to select my teammates for evaluation so that I can efficiently assess their contributions and provide feedback.(sp:4)
83 | Task 07.01 After selecting teammates, students should be redirected to the evaluation form. | 1 | 10/10/2024 | Create navigation to redirect the student to the evaluation form page upon selecting teammates. | Medium | Low | Anthony
93 | Task 07.02 Modify/design the evaluation form page. | 3 | 10/10/2024 | Design the evaluation form interface, including options for selecting teammates, providing ratings, and submitting feedback. | High | Medium | Ren-cc
US.08: As a student, I want to assess my teammates across multiple dimensions—Cooperation, Conceptual Contribution, Practical Contribution, and Work Ethic—so I can provide a more comprehensive evaluation of their performance.(sp10)
84 | Task.08.01 The evaluation form should include the following dimensions for each teammate: Cooperation Conceptual Contribution Practical Contribution Work Ethic. | 1 | 24/10/2024 | Develop a form with fields for Cooperation, Conceptual Contribution, Practical Contribution, and Work Ethic. | High | Medium | Anthony
85 | Task.08.02 Each dimension should have a 5-point rating scale (1 to 5). | 0 | 24/10/2024 | Add a rating scale input (1-5) for each dimension in the form. | Medium | Low | Anthony
86 | Task.08.03 For each dimension, provide an optional comment box where students can add qualitative feedback. | 0 | 24/10/2024 | Include comment boxes below each rating scale to capture optional feedback. | Low | Low | Anthony
87 | Task.08.04 Ensure that comments are optional and do not affect the ability to submit ratings. | 1 | 24/10/2024 | Adjust form validation to allow submission without comments. | Medium | Low | Anthony
88 | Task.08.05 The system should validate that all teammates have been rated across all dimensions before submission. | 3 | 24/10/2024 | Implement form validation to ensure every teammate is rated on each dimension before submission. | High | Medium | Anthony
89 | Task.08.06 After completing the assessment, students should see a confirmation page summarizing both ratings and comments (if provided). | 3 | 24/10/2024 | Display a summary page with details of the student's ratings and comments for each teammate. | High | Medium | Anthony
94 | Task.08.07 Design confirmation page. | 1 | 24/10/2024 | Design the layout of the confirmation page to display the teammate assessments clearly. | Medium | Low | Ren-cc
90 | Task.08.08 Once confirmed, students should receive a success message indicating their evaluation has been submitted. | 0 | 24/10/2024 | Show a success message after the confirmation page, confirming the evaluation submission. | Medium | Low | Anthony
US.09 As a developer, I want to store user and assessment data in a PostgreSQL database, so that the system can scale and provide robust data management while keeping the API unchanged for the frontend.(sp:26)
75 | Task.09.01 Set up PostgreSQL database | 8 | 21/10/2024 | Configure PostgreSQL server, create schema, and set up initial tables. | High | High | Lemonada10
76 | Task.09.02 Update Spring Boot configuration | 3 | 21/10/2024 | Configure Spring Boot to connect with PostgreSQL and manage database sessions. | High | High | Lemonada10
77 | Task.09.03 Define JPA entities | 1 | 21/10/2024 | Define JPA entity classes corresponding to the tables for storing users and assessments. | Medium | Medium | Lemonada10
78 | Task.09.04 Implement Spring Data JPA Repositories | 3 | 21/10/2024 | Create repository interfaces to interact with user and assessment data in PostgreSQL. | Medium | Medium | Lemonada10
79 | Task.09.05 Refactor Service Layer | 8 | 21/10/2024 | Implement security configurations to protect database access and prevent unauthorized modifications. | High | High | Lemonada10
80 | Task.09.06 Test API Compatibility | 3 | 21/10/2024 | Run tests to ensure that the new PostgreSQL setup functions with the existing API without breaking changes. | High | Medium | Lemonada10
US.10 As a developer, I want to ensure that the frontend React app continues to function without changes, so that the migration to PostgreSQL is seamless and transparent to users.(sp:4)
91 | Task.10.01 Test React app with migrated backend | 3 | 25/10/2024 | Verify that all frontend components continue to work as expected with the PostgreSQL database. | High | Medium | Lemonada10
92 | Task.10.02 Verify frontend data handling | 1 | 25/10/2024 | Test data retrieval and submission functions in the frontend to ensure compatibility with PostgreSQL. | Medium | Low | Lemonada10
US.11 As a developer, I want to make unit testing to make sure that all back-end functionalities are working/behaving as expected.(sp:14)
96 | Task.11.01 Implement unit testing for sign up | 5 | 27/10/2024 | Create unit tests for user sign-in functionality, ensuring security and data accuracy. | High | Medium | Mark
97 | Task.11.02 Implement unit testing for sign in | 3 | 27/10/2024 | Develop unit tests for user sign-up, verifying data integrity and validation rules. | High | Medium | DaniK1001
98 | Task.11.03 Implement unit testing for database | 3 | 27/10/2024 | Create unit tests for fetching and modifying student information. | High | High | Mark, DaniK1001, Anthony
99 | Task11.04 Implement CI/CD pipeline and connect it to back-end unit tests in order for automatic testing when merging branches | 3 | 27/10/2024 | Configure CI/CD pipeline to automatically run back-end unit tests upon code integration. | High | High | Lemonada10
Srint 3
US.12 As a developer, I want the peer evaluation review to be stored in the database (sp:5)
119 | Task 12.01: Implement frontend API to send review data to backend | 1 | 01/11/2024 | Develop a frontend API to send peer evaluation review data from the client side to the Develop a frontend API to send peer evaluation review data from the client side to the backend server. | High | Medium | Lemonada10
120 | Task 12.02: Create database schema for peer evaluation review | 3 | 01/11/2024 | Design the database schema to store peer evaluation review data, ensuring that the schema can handle all required fields and relationships. | High | High | DaniK1001
121 | Task 12.03: Implement backend API to handle peer evaluation review storage | 1 | 01/11/2024 | Build a backend API endpoint to receive review data from the frontend and save it in the database. | High | High | DaniK1001
US.013: As an instructor, I want to view a summary of all assessments (sp:6)
126 | Task 13.01: Design summary view UI on main dashboard | 1 | 04/11/2024 | Develop a user interface for the main dashboard that provides a summary view of all assessments for instructors. | High | Medium | Ren-cc
127 | Task 13.02: Implement calculation of average scores for each category | 3 | 04/11/2024 | Create functionality to calculate average scores for each assessment category, such as teamwork, communication, etc. | High | High | Anthony
128 | Task 13.03: Display count of completed assessments in summary view | 1 | 04/11/2024 | Show the number of completed assessments in the summary view to help instructors track assessment completion. | Medium | Low | Anthony
129 | Task 13.04: Connect Backend API to summary view for data retrieval | 1 | 04/11/2024 | Integrate backend API to fetch and display assessment data in the summary view UI. | High | Medium | Mark
US.14 As an instructor, I want to view detailed results of individual assessments (sp:8)
131 | Task 14.01: Design detailed assessment view layout | 3 | 06/11/2024 | Develop a UI layout for viewing detailed results of individual assessments. | High | Medium | Ren-cc
132 | Task 14.02: Display individual scores and comments for each assessment | 3 | 06/11/2024 | Implement functionality to display individual scores and instructor comments for each assessment in detail. | High | Medium | Anthony
133 | Task 14.03: Enable navigation from summary view to detailed view | 1 | 06/11/2024 | Add a navigation feature to allow instructors to click on an item in the summary view and see the detailed assessment. | Medium | Low | Anthony
134 | Task 14.05: Connect detailed view to backend API to retrieve data | 1 | 06/11/2024 | Integrate backend API to fetch and display detailed assessment data. | High | Medium | Mark
US.15 As a developer, I want to create unit tests for key components and functions (sp:21)
136 | Task 15.01: Write unit tests for average score calculation function | 3 | 08/11/2024 | Develop unit tests to verify the accuracy of the average score calculation function. | High | Medium | Lemonada10
137 | Task 15.02: Write unit tests for displaying count of completed assessments | 3 | 08/11/2024 | Create tests to verify that the count of completed assessments is displayed accurately. | Medium | Low | Lemonada10
138 | Task 15.03: Write unit tests for individual assessment display function | 3 | 08/11/2024 | Develop tests for the functionality that displays individual assessment details. | High | Medium | Lemonada10
139 | Task 15.04: Write unit tests for student and instructor sign in(front-end) | 3 | 08/11/2024 | Test back-end user sign-in functionality to ensure security and validation. | High | Medium | Lemonada10
140 | Task 15.05: Write unit tests for student and instructor sign up (front-end) | 3 | 08/11/2024 | Create tests to validate the front-end user sign-up process, ensuring that inputs are correctly handled and errors are displayed for invalid entries. | High | Medium | Lemonada10
141 | Task 15.06: Write unit tests for student and instructor sign up (back-end) | 3 | 08/11/2024 | Develop back-end tests for user sign-up functionality, ensuring proper validation and storage of user data in the database. | High | High | Mark
142 | Task 15.07: Write unit tests for student and instructor sign in (back-end) | 3 | 08/11/2024 | Develop unit tests for back-end sign-in functionality, ensuring validation of user credentials and secure authentication. | High | High | DaniK1001
143 | Task 15.08: Write unit tests for all controllers in java | 3 | 08/11/2024 | Implement unit tests for all back-end controllers, ensuring that they handle requests correctly and respond with appropriate data or error messages. | High | High | DaniK1001
US.16 As a developer, I want to limit profanity in comments and add email confirmation for signup (sp:5)
167 | Task 16.01: Implement sentiment analysis for comment fields | 3 | 10/11/2024 | Add a filtering mechanism to detect and limit profanity in comments. | Medium | Medium | DaniK1001
168 | Task 16.02: Implement mail sending algorithm in backend | 2 | 10/11/2024 | Develop a backend algorithm to send email confirmations for user signups. | High | High | Mark
PLEASE REFER TO GITHUB FOR THE ACCEPTANCE CRITERIA